## ServerData sheet usage
xlgantt_reserved | project_information | xlgantt_task_connection | xlgantt_task_id | wbs_level | WBS | Task | Note | Start | Finish | __Memo | Calendar | Total Work | Planned Work | Total Duration | Planned Duration | Actual Start | Actual Finish | Actual Total Work | Actual Total Duration | Weight | Resources | Deliverables | Planned %Work Complete | %Work Complete
| XYZ System | 1;3;4;0;1 | 1 | 1 | 1 | Project XYZ |  | 2019-09-16 | 2019-11-22 | [13 empty] | 0 | 0
| 2019-09-01 | 2;4;8;0;1 | 2 | 2 | 1.1 | Analysis |  | 2019-09-16 | 2019-09-20 | [13 empty] | 0 | 0
| 2019-11-30 | 3;5;6;0;0 | 3 | 3 | 1.1.1 | Define scope |  | 2019-09-16 | 2019-09-19 | [11 empty] | Elsa |  | 100% | 100%
| 45% | 4;8;9;0;1 | 4 | 3 | 1.1.2 | Confirm scope |  | 2019-09-20 | 2019-09-20 | Prepare review materials | [12 empty] | 100% | 100%
| 43.33% | 5;7;11;0;1 | 5 | 3 | 1.1.3 | Benchmarking |  | 2019-09-16 | 2019-09-18 | [11 empty] | Elsa |  | 0 | 0
|  | 6;11;12;0;1 | 6 | 3 | 1.1.4 | Workshop |  | 2019-09-19 | 2019-09-20 | [11 empty] | Elsa |  | 0 | 0
|  | 7;10;14;0;1 | 7 | 2 | 1.2 | Design |  | 2019-09-23 | 2019-10-11 | [13 empty] | 0 | 0
|  | 8;14;15;0;1 | 8 | 3 | 1.2.1 | Design Database |  | 2019-09-23 | 2019-09-27 | [11 empty] | John |  | 0 | 0
|  | 9;15;16;0;1 | 9 | 3 | 1.2.2 | Design UI |  | 2019-09-30 | 2019-10-11 | [11 empty] | John |  | 0 | 0
|  |  | 10 | 2 | 1.3 | Development |  | 2019-10-14 | 2019-11-08 | [13 empty] | 0 | 0
|  |  | 11 | 3 | 1.3.1 | Coding |  | 2019-10-14 | 2019-11-01 | [13 empty] | 0 | 0
|  |  | 12 | 3 | 1.3.2 | Perform unit tests |  | 2019-11-04 | 2019-11-08 | [11 empty] | Mike |  | 0 | 0
|  |  | 13 | 2 | 1.4 | Testing |  | 2019-11-11 | 2019-11-22 | [13 empty] | 0 | 0
|  |  | 14 | 3 | 1.4.1 | Perform integration test |  | 2019-11-11 | 2019-11-15 | [11 empty] | Mike,Elsa |  | 0 | 0
|  |  | 15 | 3 | 1.4.2 | Perform system test |  | 2019-11-18 | 2019-11-20 | Prepare testing tool | [10 empty] | John |  | 0 | 0
|  |  | 16 | 3 | 1.4.3 | Perform UAT |  | 2019-11-21 | 2019-11-22 | [11 empty] | Bob |  | 0 | 0
Do not enter. The title "xlgantt_reserved" should be entered in cell A1, and there should be no value from line 2. When the import is completed, the results are displayed in lines 2 and 3. | Optional input Line 2: Project name Line 3: Project start date Line 4: Project finish date Line 5: Project planned %work complete Line 6: Project %work complete | Optional input id;source;target;type;criticalPath id: Connector ID (numbering in order) source: xlgantt_task_id (prior task) target: xlgantt_task_id (following task) type: 0-FS, 1-FF, 2-SS, 3-SF criticalPath: 1-critical path, 0-not critical path | Required input numbering in order | Required input Enter wbs_level as a number | Optional input | Required input | Optional input | Required input | Required input | Optional input User defined fields have two underscores in front of the field name | Optional input | Optional input | Optional input | Optional input | Optional input | Optional input | Optional input | Optional input | Optional input | Optional input | Optional input | Optional input | Optional input | Optional input